## Sheet1
INSIGHT REPORT
Project details :
PROJECT STATUS |  | REPORT DATE
GREEN |  | 12th January 2024
RELEASE VERSION | CURRENT STAGE | NEXT MILESTONE
2.2.0 GA | In QA | Dev& QA (Code Lock)
PROJECT DESCRIPTION
Insight 2.2.0 Release
Release Details :
PHASE | STATUS | PLANNED RELEASE DATE | ACTUAL RELEASE DATE
DEV | InProgress | 12th January 2024
QA | InProgress | 18th January 2024
Dev& QA (Code Lock) | Not-Started | 18th January 2024
Regression | Not-Started | 23rd January 2024
Migration | Not-Started | 23rd January 2024
IQC | Not-Started | 25th January 2024
RTM | Not-Started | 29th January 2024
GA Path | Not-Started | 5th February 2024
Highlights:
HIGHLIGHTS
Testing completed for 7 Features.
Around 60 Defects were found in QA phase.
API Automation of Sanity test cases for GDA features has been integrated with existing Sanity Suite.
Feature Status :
Feature | Status | Remarks
Audit Log Report | Completed | QA Completed
SPT Report | Completed | QA Completed
Config Alerts | Completed | QA Completed
Commission Report | Completed | QA Completed
Decommission Report | Completed | QA Completed
Serial Number Report | Completed | QA Completed
Audit Log Tableau Dashboard | Completed | QA Completed
Lot Event details Tableau Dashboard | InProgress | 60% Testing completed
Alarms Tableau Dashboard | InProgress | 90% Testing completed
Risk Tracker:
SL# | Identified Risk | Status | Severity | Impact | Mitigation | Closure required by | Owner
Defect Trend :
Feature | Jira ID | Description | Status | DEV Owner | Severity | ETA
GDA Data Migration Utility | SPHERE-10159 | (GDA) Add Version Check (example Python Utility SQL Query Error Line 2660) | Fixed | Roy, Ankit | 2 | 2024-01-12
Total Defects | Blocker (S1) | Severe (S2) | Moderate (S3) | Minor (S4,S5)
60 | 15 (15/15) | 20 (19/20) | 19 (17/19) | 6 (6/6)
QA Test Execution Status :
Feature | Total Test Case | #Executed | #Pass | #Fail | Remarks
Audit Log Report Backend | 44 | 44 | 44 |  | Completed
Audit Log Report UI | 7 | 7 | 7 |  | Completed
Decommission Report Backend | 30 | 30 | 29 | 1 | Completed
SPT Report UI | 2 | 2 | 2 |  | Completed
SPT Report Backend | 17 | 15 | 15 |  | Completed
Commission Report Backend | 15 | 15 | 14 | 1 | Completed
Commission Report UI | 5 | 5 | 5 |  | Completed
Decommission Report UI | 2 | 2 | 2 |  | Completed
Serial Number Report UI | 4 | 4 | 4 |  | Completed
Serial Number Report Backend | 17 | 17 | 17 |  | Completed
Audit Log Tableau Dashboard | 7 | 7 | 6 | 1 | Completed
Lot Event details Tableau Dashboard | 7 | 5 | 5 |  | In-progress
Alarms Tableau Dashboard | 8 | 7 | 6 | 1 | In-progress