## Sheet1
INSIGHT REPORT
Project details :
PROJECT STATUS |  | REPORT DATE
GREEN |  | 13th January 2024
RELEASE VERSION | CURRENT STAGE | NEXT MILESTONE
2.2.0 GA | Code Lock | Regression
PROJECT DESCRIPTION
Insight 2.2.0 Release
Release Details :
PHASE | STATUS | PLANNED RELEASE DATE | ACTUAL RELEASE DATE
DEV | Completed | 12th January 2024 | 17th January 2024
QA | Completed | 18th January 2024 | 18th January 2024
Dev& QA (Code Lock) | Completed | 18th January 2024 | 18th January 2024
Migration | Not-Started | 23rd January 2024
Regression | Not-Started | 23rd January 2024
IQC | Not-Started | 25th January 2024
RTM | Not-Started | 29th January 2024
GA Path | Not-Started | 5th February 2024
Highlights:
HIGHLIGHTS
QA completed for 2.2.0 Features.
Code lock done on Inisght Version: 2.2.0Build number: 20240118-044642
Around 61 Defects were found in QA phase.
Feature Status :
Feature | Status | Remarks
Audit Log Report | Completed | QA Completed
SPT Report | Completed | QA Completed
Config Alerts | Completed | QA Completed
Commission Report | Completed | QA Completed
Decommission Report | Completed | QA Completed
Serial Number Report | Completed | QA Completed
Audit Log Tableau Dashboard | Completed | QA Completed
Lot Event details Tableau Dashboard | Completed | QA Completed
Alarms Tableau Dashboard | Completed | QA Completed
Risk Tracker:
SL# | Identified Risk | Status | Severity | Impact | Mitigation | Closure required by | Owner
Defect Trend :
Open Defects (S1/S2)
Feature | Jira ID | Description | Status | DEV Owner | Severity | ETA
Agent Installer | SPHERE-10225 | 2.2.0 Agent Installer : Systech services are not enabled post installing latest Agent Installer | In-Progress | K M, Arya Jayadev | 1 | 20th January 2024
Total Defects | Blocker (S1) | Severe (S2) | Moderate (S3) | Minor (S4,S5)
61 | 16 (15/16) | 20 (20/20) | 19 (19/19) | 6 (6/6)
QA Test Execution Status :
Feature | Total Test Case | #Executed | #Pass | #Fail | Remarks
Audit Log Report Backend | 44 | 44 | 44 |  | Completed
Audit Log Report UI | 7 | 7 | 7 |  | Completed
Decommission Report Backend | 30 | 30 | 30 |  | Completed
SPT Report UI | 2 | 2 | 2 |  | Completed
SPT Report Backend | 17 | 15 | 15 |  | Completed
Commission Report Backend | 15 | 15 | 15 |  | Completed
Commission Report UI | 5 | 5 | 5 |  | Completed
Decommission Report UI | 2 | 2 | 2 |  | Completed
Serial Number Report UI | 4 | 4 | 4 |  | Completed
Serial Number Report Backend | 17 | 17 | 17 |  | Completed
Audit Log Tableau Dashboard | 7 | 7 | 7 |  | Completed
Lot Event details Tableau Dashboard | 7 | 7 | 7 |  | Completed
Alarms Tableau Dashboard | 8 | 8 | 8 |  | Completed