## Sheet1
UNISECURE REPORT
Project details :
PROJECT STATUS |  | REPORT DATE
YELLOW |  | 29TH NOV 2023
RELEASE VERSION | CURRENT STAGE | NEXT MILESTONE
2.1.0 | In QA | Dev-QA Code Freeze 13th Oct 2023
PROJECT DESCRIPTION
GMP-Archival feature is not complete and in Implementation phase.
SEV2 Tickets in open status are delaying QA closure on Feature Testing. DEV ETA for Defect Closure is 20th Oct .
Release Details :
ENVIRONMENT | STATUS | PLANNED RELEASE DATE | ACTUAL RELEASE DATE
DEV | InProgress | 3rd October 2023
QA | InProgress | 17th October 2023
Regression | Not Started | 19th October 2023
Migration | Not Started | 19th October 2023
IQC | Not Started | 20th October 2023
RTM | Not Started | 6th November 2023
GA | Not Started | 13th November 2023
Highlights:
HIGHLIGHTS
QA completed for 6 Feature
Software update Feature Testing closure is dependent on open Sev2 Defects.
GMP-Archival QA Testing is deferred due to Dev completion. We have been in war room and making progress on implementation.
Feature Status :
Feature | Status | Remarks
Diagnostic viewer | Completed | Guardian/ Advisor/Sentri - Completed Testing -
Uniseries real time processing - Alarms, Counters | Completed | Need to Retest 1 defect.
Config Alerts | Completed | QA Completed
GMP Batch Records - IOD flows for Alarms/Events/Audit | Completed
GMP Data Archival | InProgress | In Implementation Phase.
All UX 2.0 work to be done - Manage Assets(Software Updates) | InProgress | ETA : 25th Oct . QA Closure depends on Defect fix - SPHERE-9665
- Info center | Completed | QA Completed
- Software Center | Completed | Major issues resolved .
- Managed scenes | Completed | QA Completed
Risk Tracker:
SL# | Identified Risk | Status | Severity | Impact | Mitigation | Closure required by | Owner
1 | GMP Archival Feature | Open | Critical | The risk to RTM of 2.1.0 | Feature should be delivered by 27th Oct 2023 | 27th Oct 2023 | Raghu
Defect Trend :
Feature | Jira ID | Description | Status | DEV Owner | Severity | ETA
Software Update | SPHERE-9477 | Advanced filter on Manage Assets is not filtering nodes properly | Open | Bhite, Yogesh | 2 | 20th Oct
| SPHERE-9665 | Downloading of uniseries version not working in S/w Updates | Open | Bhite, Yogesh | 2 | 20th Oct
Real time Dashboard | SPHERE-9610 | Packed column is not displayed in Real time Dashboard | Open | Bhite, Yogesh | 2 | 20th Oct
Total Defects | Blocker (S1) | Severe (S2) | Moderate (S3) | Minor (S4,S5)
37 | 2 | 18 | 13 | 5
QA Test Execution Status :
Feature | Total Test Case | #Executed | #Pass | #Fail | Remarks
Manage scenes | 26 | 26 | 26 |  | Completed
Info center | 7 | 7 | 6 | 1 | Completed
Software Center | 5 | 5 | 4 | 1 | Completed
Manage Assets(Software Updates) | 5 | 5 | 1 | 4 | not completed
Diagnostic viewer(Only Guardian Completed) | 16 | 16 | 15 | 1 | Completed
Config Alerts | 18 | 18 | 18 |  | Completed
GMP Batch Records - IOD flows | 19 | 19 | 19 |  | Completed
Uniseries real time processing - Alarms | 2 | 2 | 2 |  | Completed with Known issues SPHERE-9597
Real time counts Packaging Dashboard_Test Design | 4 | 2 | 1 | 1 | 2 Test case not applicable