## Sheet1
Insight REPORT
Project details :
PROJECT STATUS |  | REPORT DATE
GREEN |  | 15th Dec 2023
RELEASE VERSION | CURRENT STAGE | NEXT MILESTONE
2.2.0 Betal Version | Completed | GA Path - In Progress
PROJECT DESCRIPTION
2.2.0 Build deployed to Guest Sandbox
2.2.0 handover for Security Assessment completed
Release Details :
ENVIRONMENT | STATUS | PLANNED RELEASE DATE | ACTUAL RELEASE DATE
DEV | Completed | 30th November 2023 | 30th November 2023
QA | Completed | 8th December 2023 | 8th December 2023
Regression | NA | NA
Migration | NA | NA
IQC | NA | NA
RTM | NA | NA
Beta | Completed | 19th December 2023 | 12th December 2023
Highlights:
HIGHLIGHTS
Build deployed to Guest Sandbox with known issues.
QA completed 1 round of testing for all the GMP features . Defect validation of open issues and further changes will be tracked as part of 2.2.0 GA.
All test cases have been executed one round post review.
Migration, regression and IQC are excluded since 2.2.0 is of Beta Release.
Security Assessment of 2.2.0 has been initiated.
Feature Status :
Feature | Status | Remarks
Audit Log Report | Completed
SPT Report | Completed
Commission Report | Completed
Decommission Report | Completed
Serial Number Report | Completed
Risk Tracker:
SL# | Identified Risk | Status | Severity | Impact | Mitigation | Closure required by | Owner
1 | Issues observed in PDF generation. Tool yet to be finalised | Completed | Critical | Risk to RTM of 2.2.0 | New pdf tool has been implemented to generate reports, awaiting change in qa env (COD Dec 6th ) | 6th Dec 2023 | Raghu
2 | Performance issue observed in Lot Data Archival | Completed | High | Risk to RTM of 2.2.0 | New scripts under test. We have discussed options to improve performance of scripts to upload partial data | 6th Dec 2023 | Vladimir MEDVEDEV
Defect Trend :
Feature | Jira ID | Description | Status | DEV Owner | Severity | ETA
Python Utility | SPHERE-9858 | User login and AWS S3 credentials are not encrypted in config file | Completed | K M, Arya Jayadev | 2
GDA Serial Report | SPHERE-10134 | Amgen Data Observation : Same Serial Number with multiple LOTID/itemID | Completed | K M, Arya Jayadev | 2
Total Defects | Blocker (S1) | Severe (S2) | Moderate (S3) | Minor (S4,S5)
57 | 14 | 19 | 17 | 7
QA Test Execution Status :
Feature | Total Test Case | #Executed | #Pass | #Fail | Remarks
Audit Log Report Backend | 44 | 44 | 43 | 1
Audit Log Report UI | 7 | 7 | 7
Decommission Report Backend | 30 | 30 | 29 | 1
SPT Report UI | 2 | 2 | 2
SPT Report Backend | 17 | 15 | 14 | 1
Commission Report Backend | 15 | 15 | 14 | 1
Commission Report UI | 5 | 5 | 5
Decommission Report UI | 2 | 2 | 2
Serial Number Report UI | 4 | 4 | 4
Serial Number Report Backend | 17 | 17 | 16 | 1