## Sheet1
UNITRACE REPORT
Project details :
PROJECT STATUS |  | REPORT DATE
GREEN |  | 9th Jan 2024
RELEASE VERSION | CURRENT STAGE | NEXT MILESTONE
Cloud - 9.5.0 & Mobile 2.0.0 | Completed | GA Path - In Progress
PROJECT DESCRIPTION
UniTrace cloud 9.5.0 and mobile 2.0.0 release
Key highlights of Release
SQS implementation & backend autoscaling
UT Mobile - Camera & Multi-Scan & AR
Release Details :
ENVIRONMENT | STATUS | PLANNED RELEASE DATE | ACTUAL RELEASE DATE
DEV | Completed | 25th September 2023 | 15th December 2023
QA | Completed | 25th September 2023 | 15th December 2023
Regression | Completed | TBD | 20th December 2023
Migration | Completed | TBD | 18th December 2023
IQC | Completed | TBD | 21st December 2023
RTM | Completed | 11th October 2023 | 22nd December 2023
GA | In Progress | 18th October 2023 | 8th January 2024
Highlights:
HIGHLIGHTS
QA completed for 10 Features
Key Highlights
SQS Implementation & backend autoscaling
UT Mobile - Camera & Multi-Scan & AR
Feature Status :
Feature | Status | Remarks
Camera & Multi-Scan & AR - Business Step Camera MultiScan | Completed | QA Completed
Camera & Multi-Scan & AR - AR Display | Completed | QA Completed Open Issue : Defect Logged as MTRC-239 (Sev-3)
Camera & Multi-Scan & AR - Barcode Encoding Selection | Completed | QA Completed
Camera & Multi-Scan & AR - Item Verification Camera MultiScan | Completed | QA Completed Open Issue : Defect Logged as MTRC-257 (Sev-4) | `
Add Camera View Button to Scanned Items Screen - QA | Completed | QA Completed
Mobile Device Field Dropdowns - QA | Completed | QA Completed
Mobile Tracing Dashboard - QA | Completed | QA Completed Open Issue : Defect Logged as MTRC-268 (Sev-3) , TRACE-11546(Sev-3)
Verify Upgrade from Play Store | Completed | QA Completed
Verify Minimum Cloud Version of 9.5.0 | Completed | QA Completed
Business Step Options - DB Verification Bypass | Completed | QA Completed
Business Step Options - AI Codes Parsing & Free Format | Completed | QA Completed Open Issue : Defect Logged as MTRC-333 (Sev-3) , MTRC-306 (Sev-3)
Job Format Routing - QA | Completed | QA Completed
Inbound Shipment Notification | Completed | QA Completed
XSD Validation Handler | Completed | QA Completed
AS2 Volume Testing | Completed | QA Completed
HTTPS Volume Testing | Completed | QA Completed
Regression Testing of MultiTenant SingleRDS Environment with SQS | Completed | QA Completed
Functional Regression Testing of SQS Implementation | Completed | QA Completed
SQS test run on Multitenant Environment | Completed | QA Completed
Autoscaling testing | Completed | QA Completed
Multi Tenant Single DB - functional testing | Completed | QA Completed
AS2 Transfer Handler - Add File Extension Parameter | Completed | QA Completed Open Issue : Defect Logged as TRACE-12624 (Sev-3)
Risk Tracker:
SL# | Identified Risk | Status | Severity | Impact | Mitigation | Closure required by | Owner
1 | Migration scenario where in multi-tenant multi RDS needs to be migrated to multi-tenant single RDS was deferred from 9.5.0 and will be included in a future release | Open | Critical | This is a risk provided with RTM notification for 9.5.0 | Feature should be delivered by future release | TBD | Brian
Defect Trend :
Feature | Jira ID | Description | Status | DEV Owner | Severity | ETA
Mobile Tracing Dashboard - QA | MTRC-268 | MTRC ¦ User is required to perform login steps on web page | Open | Sharma, Deewankshi | 3
Mobile Tracing Dashboard - QA | TRACE- 11546 | Unitrace-qa ¦ MTRC ¦ Mobile responsive issue when number of quick links assigned to user is more | Open | Levy, Brian | 3
Business Step Options - AI Codes Parsing & Free Format | MTRC-333 | MTRC ¦ With "Free Format" enabled in Business Step, upon scanning and submitting the Code-128 2D Barcode, Job is getting failed with error. Also, in Receipt, item is not displayed as per the Free Format under EPC tag | Open | Levy, Brian | 3
Business Step Options - AI Codes Parsing & Free Format | MTRC-306 | UniTrace Cloud App ¦ On Job Queue page, Device information is not getting displayed for job executed via UniTrace Mobile App | Open | Levy, Brian | 3
AS2 Transfer Handler - Add File Extension Parameter | TRACE-12624 | user is able to create & download file other than Supported Formats: .csv, .xml, .json, .txt, .job using inbound job API having AS2 Transfer handler job format | Open | Kumar M Nandha | 3
Total Defects | Blocker (S1) | Severe (S2) | Moderate (S3) | Minor (S4,S5)
78 | 2 | 35 | 33 | 8
QA Test Execution Status :
Feature | Total Test Case | #Executed | #Pass | #Fail | Remarks
Camera & Multi-Scan & AR - Barcode Encoding Selection | 4 | 4 | 4 |  | Completed
Job Format Routing - QA | 4 | 4 | 4 |  | Completed
Mobile VRS Dashboard - QA | 6 | 6 | 6 |  | Completed
Mobile Tracing Dashboard - QA | 4 | 4 | 1 | 3 | Completed with Known issues MTRC-268 (Sev-3) , TRACE-11546(Sev-3)
Camera & Multi-Scan & AR - AR Display | 6 | 6 | 4 | 2 | Completed with Known issue MTRC-239 (Sev-3)
Camera & Multi-Scan & AR - Item Verification Camera MultiScan | 11 | 11 | 10 | 1 | Completed with Known issue MTRC-257 (Sev-4)
Business Step Options - DB Verification Bypass | 7 | 7 | 7 |  | Completed
Business Step Options - AI Codes Parsing & Free Format | 4 | 4 | 3 | 1 | Completed with Known issues MTRC-333 (Sev-3) , MTRC-306 (Sev-3)
Mobile VRS - QA | 14 | 14 | 14 |  | Completed
Verify Minimum Cloud Version of 9.5.0 | 4 | 4 | 4 |  | Completed
Add Camera View Button to Scanned Items Screen - QA | 3 | 3 | 3 |  | Completed
UniTrace Mobile - Non Default Orientation Support - QA | 1 | 1 | 1 |  | Completed
Inbound Shipment Notification | 8 | 8 | 8 |  | Completed
XSD Validation Handler | 2 | 2 | 2 |  | Completed
AS2 Transfer Handler - Add File Extension Parameter | 1 | 1 | 1 |  | Completed